# G&J Pepsi — IT Infrastructure Upgrade Plan

Prepared by: Todd Seufer, Director of Product Development & Daniel Foster, Sr Director of IT

# Overview

This plan outlines G&J Pepsi’s phased migration from on-premises infrastructure to a hybrid cloud environment. The upgrade addresses aging hardware, security vulnerabilities, and the need for improved scalability to support our growing digital operations. The project spans 12 months with a total budget of $1.8M.

# Current State Assessment

Primary data center: on-premises at corporate headquarters (8 years old)

ERP system: SAP S/4HANA running on aging Dell PowerEdge servers

Email and collaboration: Microsoft 365 (already cloud-based)

Warehouse Management System (WMS): Manhattan Associates, on-premises

Network: Hub-and-spoke architecture connecting 5 DCs to corporate

Backup: On-site tape backup with off-site monthly rotation

Known issues: 3 unplanned outages in past 12 months; server utilization at 87% peak

# Proposed Architecture

## Phase 1: Foundation (Months 1-4)

Migrate file servers and backup infrastructure to Azure

Deploy Azure Site Recovery for disaster recovery

Upgrade network backbone to SD-WAN for improved DC connectivity

Implement Azure Active Directory for unified identity management

Budget: $520,000

## Phase 2: Core Applications (Months 4-8)

Migrate SAP S/4HANA to Azure Virtual Machines

Upgrade WMS to Manhattan Associates cloud-hosted version

Implement Azure SQL for reporting databases

Deploy Microsoft Defender for Cloud across all workloads

Budget: $780,000

## Phase 3: Optimization (Months 8-12)

Decommission on-premises servers

Implement Azure Monitor and Log Analytics for proactive monitoring

Deploy Power BI dashboards connected to cloud data sources

Optimize cloud costs through reserved instances and right-sizing

Budget: $500,000

# Impact on Operations

## What Employees Will Notice

Faster application performance (projected 40% improvement in SAP response time)

Improved remote access for field and corporate staff

Single sign-on across all applications (no more multiple passwords)

New Power BI dashboards for real-time operational reporting

Brief scheduled maintenance windows during migration (weekend nights only)

## What Won’t Change

Microsoft 365 (Outlook, Teams, Word, Excel) — already cloud-based, no impact

Daily workflows and business processes remain the same

User interfaces for SAP and WMS will look the same

## Planned Downtime

| Phase | Affected Systems | Downtime Window | Impact |
| --- | --- | --- | --- |
| Phase 1 | File servers, backup | Saturday 10 PM - Sunday 6 AM | No access to shared drives for 8 hours |
| Phase 2 | SAP, WMS | Saturday 8 PM - Sunday 8 AM | No ERP or WMS access for 12 hours (2 weekends) |
| Phase 3 | Reporting databases | Saturday 10 PM - Sunday 4 AM | Reports unavailable for 6 hours |

# Security Improvements

Multi-factor authentication (MFA) enforced for all users

Zero-trust network architecture replacing traditional VPN

Automated threat detection with Microsoft Defender for Cloud

Encrypted data at rest and in transit (AES-256)

SOC 2 Type II compliance for cloud infrastructure

Automated backup with 99.99% availability SLA

# Budget Summary

| Phase | Cost | Timeline |
| --- | --- | --- |
| Phase 1: Foundation | $520,000 | Months 1-4 |
| Phase 2: Core Applications | $780,000 | Months 4-8 |
| Phase 3: Optimization | $500,000 | Months 8-12 |
| Total | $1,800,000 | 12 months |

Projected annual savings from decommissioning on-premises infrastructure: $320,000/year (hardware maintenance, power, cooling, physical security).