# G&J Pepsi — Route Optimization Proposal

Prepared by: Jason Lester, Director of Supply Chain | Date: January 2026

# Executive Summary

This proposal outlines a comprehensive route optimization initiative for G&J Pepsi’s distribution network. By implementing AI-powered route planning software and restructuring our delivery territories, we project annual savings of $1.2M in fuel costs, a 15% reduction in delivery miles driven, and a 12% improvement in on-time delivery rates. The project requires a $450,000 investment and an 8-month implementation timeline.

# Problem Statement

G&J Pepsi currently operates 85 delivery routes across 5 distribution centers serving approximately 4,200 retail, convenience, and foodservice accounts. Our current route planning process relies on static territories assigned annually, with limited real-time adjustment capability.

## Current Challenges

Routes were last restructured 3 years ago; account distribution has shifted significantly

Average route efficiency is 68% (industry benchmark: 82%)

Fuel costs increased 18% year-over-year due to inefficient routing

Drivers report an average of 45 minutes of non-productive drive time per route

Peak season (summer months) creates bottlenecks that lead to missed deliveries

No integration between route planning and real-time traffic/weather data

# Proposed Solution

## Phase 1: Technology Implementation (Months 1-3)

Deploy Descartes Route Planner with AI optimization engine

Integrate with existing fleet GPS and telematics systems

Connect to real-time traffic data APIs

Configure customer delivery windows and service time parameters

Cost: $280,000 (software licensing, integration, configuration)

## Phase 2: Territory Redesign (Months 3-5)

Use AI analysis to restructure all 85 routes based on current account distribution

Balance route workload to reduce overtime

Create dynamic routing capability for peak season flexibility

Pilot in Southeast region (Atlanta DC, Orlando DC) before full rollout

Cost: $90,000 (consulting, change management, driver training)

## Phase 3: Full Deployment & Optimization (Months 5-8)

Roll out optimized routes to all 5 distribution centers

Train all drivers and dispatchers on new system

Implement continuous optimization with weekly route reviews

Deploy mobile app for drivers with turn-by-turn optimized navigation

Cost: $80,000 (training, mobile deployment, ongoing support)

# Expected Benefits

| Benefit | Current State | Projected State | Annual Impact |
| --- | --- | --- | --- |
| Fuel costs | $3.8M/year | $2.6M/year | $1.2M savings |
| Miles driven | 4.2M miles/year | 3.6M miles/year | 15% reduction |
| Route efficiency | 68% | 82%+ | 14+ point improvement |
| On-time delivery | 95.2% | 97.5%+ | 2.3+ point improvement |
| Driver overtime | 12.4% of total hours | 8.0% of total hours | $340K savings |
| Vehicle wear/maintenance | $890K/year | $750K/year | $140K savings |

Total projected annual benefit: $1.68M | Payback period: 3.2 months

# Implementation Timeline

| Phase | Timeline | Key Milestones | Owner |
| --- | --- | --- | --- |
| Phase 1: Technology | Jan - Mar 2026 | Software deployed, GPS integration complete, testing done | IT + Supply Chain |
| Phase 2: Territory Redesign | Mar - May 2026 | AI analysis complete, Southeast pilot live, results validated | Supply Chain + Ops |
| Phase 3: Full Deployment | May - Aug 2026 | All 5 DCs live, drivers trained, continuous optimization active | Operations |

# Risks and Mitigations

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Driver resistance to route changes | High | Medium | Early communication, involvement in pilot, incentive for adoption |
| Integration delays with legacy GPS | Medium | High | Dedicated IT resource; backup manual routing plan |
| Customer delivery window conflicts | Medium | Medium | Customer communication plan; phased territory changes |
| Peak season disruption during rollout | Low | High | Schedule Phase 3 to complete before June peak |
| Software vendor support issues | Low | Medium | SLA requirements in contract; dedicated account manager |

# Budget Summary

| Category | Cost |
| --- | --- |
| Software licensing and integration | $280,000 |
| Consulting and territory redesign | $90,000 |
| Training and deployment | $80,000 |
| Contingency (10%) | $45,000 |
| Total Investment | $450,000 (one-time) + $85,000/yr licensing |

# Recommendation

We recommend proceeding with this initiative immediately, beginning Phase 1 in January 2026. The projected ROI of 373% in the first year, combined with significant operational improvements in on-time delivery and driver satisfaction, makes this a high-priority investment. We request approval of the $450,000 budget and assignment of a cross-functional project team from IT, Supply Chain, and Operations.